## Sheet1
Task Description | IBM Task Description | Resource | Start date | End date | Status
Re-provision
Reprovision the appliance to CPD 4.0.6 and CPDS 2.0.1.1 | Appliance Installation | IBM
Install NPS | Appliance Installation | IBM
Install Watson Studio Service | Appliance Installation | IBM
Install Watson Machine Learning Service | Appliance Installation | IBM
Setup GitHub Repos in new environment
Obtain a list of Repos | Identification/Selection of Subset (i.e., 10) of WSL Projects - Client | BCBS SC? Jameson
Submit request to github to have repos created | Appliance Installation | BCBS SC? A. Marshall
Build repos | Appliance Installation | IBM
Create new AD groups for accessing repos (if not using existing AD groups) | Appliance Installation | IBM
Ensure configurations are accurate on new repository | Appliance Installation | IBM
Migrate existing modules from Watson Studio Local to Watson Studio Service | Identification/Selection of Subset (i.e., 10) of WSL Projects | IBM/Don/Jameson
Configure Watson Studio Service to utilize active directory groups associated with roles within Watson Studio Service | Appliance Installation | IBM
Configure Watson Machine Learning Service to utilize active directory groups associated with roles within Watson Machine Learning Service | Appliance Installation | Bob Dissinger and IBM
Configure and validate integration of Watson Studio Service with GitHub Enterprise | Appliance Installation | Don/IBM
Configure and validate connection of Watson Studio Service to network shared drive | Appliance Installation | Don/IBM
Configure and validate connection of Watson Studio Service to CM8 | Appliance Installation | Don/IBM
Configure and validate connection of Watson Studio Service to DB2P on ZOS | Appliance Installation | Don/IBM
Configure and validate connection of Watson Studio Service to Netezza Performance Server | Appliance Installation | Don/Tom/IBM
Configure and validate connection of Watson Studio Service to Hive | Appliance Installation | Don/IBM
Configure and validate connection of Watson Studio Service to BlueVue | Appliance Installation | Don/Tom
Create process to allow Artifactory to access and store R-Cran and Anaconda packages | N/A | Backlog
NPS
Customer area will delete obsolete databases and tables on existing PDA | Data Migration and Validation - Production | Tom/Don
Install TSM in the new environment | Data Migration and Validation - Production | Ralph
DBA will work with IBM to configure test Netezza Performance DBMS on test Netezza Performance Server | NPS System Customization - Dev | IBM/Andy/Tom
Stand up vFiler to support the Backup/Restore | Data Migration and Validation | Matt Stugart
DBA will backup remaining databases and tables on existing PDA and restore them to Netezza Performance DBMS | Data Migration and Validation | Tom/Don
Copy existing Netezza load jobs on existing PDA to production Netezza Performance Server | DDL, Stored Procs, Users/Groups, UDFs - Production | IBM/Don
Copy existing configuration files from existing PDA to production Netezza Performance Server | DDL, Stored Procs, Users/Groups, UDFs - Production | IBM/Don
Create service account for running weekly load jobs on production Netezza Performance Server (leverage existing) | DDL, Stored Procs, Users/Groups, UDFs - Production | IBM/Don/Tom
Create friendly URL's for the customer to use | Data Migration and Validation | Network
Update Netezza JDBC and ODBC drivers for Watson Studio Service (Confirm with install) | Production Customer | IBM/Don
Update Netezza JDBC and ODBC drivers for Data Lake cluster | Production Customer | Gopu Rajasekharan
Update Netezza JDBC and ODBC drivers for Tableau server | Production Customer | Gary Hammell
Download driver to shared drive |  | Don Cope
Install on test server |  | Gary Hammell
Test new driver to access NPS |  | Gary Hammell
Testing of the Tableau desktop application's ability to access NPS |  | Jameson Sofge
Update Netezza JDBC and ODBC drivers for Blue Cross workstations | Production Customer | Wendy Bauman
Dowload driver to shared drive |  | Don Cope
Open tickets to install on workstations |  | Antoine Clark
Deploy new driver to workstations |  | Workstation Support
Configure role-based access control in Netezza Performance Server | NPS System Customization - Production | Don
Configure data load to Netezza Performance Server | Production Customer | Don
Send email to impacted users of Watson Studio to begin using CP4D 11/12 | Production Customer | Chris Ferres
Users begin using CP4D for the workload not dependent on persistent storage | Production Customer | Customers
Tom will work with Jameson to migrate the databases and tables for NPS | Data Migration and Validation - Production | Tom/Jameson
Jameson will repoint workloads to new Netezza as they are moved over | Data Migration and Validation - Production | Jameson Sofge
Disable accounts in Watson Studio Local who are not dependent on persistent storage | Production Customer | Don Cope
Post Version 4.0.6 - Verification Tasks
Customer regression testing | Production Customer | IBM/Don
Customer to begin using Cloud Pak for all remaining workloads | Production Customer | Jameson Sofge
Disable all remaining user accounts in old system | Production Customer | Don Cope
Decomission
Decommission existing test PDA appliances | Return to IBM | Al Green/Facilities
Decommission existing production PDA appliances | Return to IBM | Al Green/Facilities
Decommission existing test Watson Studio Local servers | N/A | Al Green
Decommission existing production Watson Studio Local servers | N/A | Al Green
Capture and transmit Cloud Pak for Data System licensing information into HCL BigFix | Appliance Installation | Doug Huddle
Environmental Monitoring
Monitor availability of Cloud Pak for Data System | NPS System Customization - Production | ITBS
Monitor availability of Netezza Performance Server | NPS System Customization - Production | ITBS